## Sheet1
Task |  | Reg no. | Weeks allocated | SPC Dates
Deciding to do a Neighbourhood Plan
1 | Town or Parish Council decides to consider preparing a NP |  | 2 | 2015-03-04
2 | Discuss proposal with MKC Development Plans team |  | 1 | 2015-03-01
3 | Set up Steering Committee and Project Team |  | 3 | 2016-01-01
Deciding on the scope of the Neighbourhood Plan
4 | Prepare for issues consultation with community |  | 4 | 2015-10-01
5 | Issues consultation with community |  | 4 | 2015-12-01
6 | Review outcomes of issues consultation |  | 2 | 2015-02-01
Designating Plan Area
7 | Decide area to be covered by plan |  | 2 | 2015-03-01
8 | Town or Parish Council submit plan area to MKC | 5 | 1 | 2015-04-01
9 | MKC publicises plan area | 6 | 1 | 2015-05-01
10 | Consultation - 6 weeks |  | 6 | 2015-06-01
11 | MKC designates plan area | 7 | 1 | 2015-06-01
Sustainability Appraisal Scoping Report
12 | Meet with MKC Development Plans to discuss SA |  | 1
13 | SA Scoping Report preparation |  | 5
14 | Send to Statutory Bodies |  | 1
15 | Consultation - 5 weeks |  | 5
16 | Comments back, amendments made to SA Framework |  | 1
Developing Options
17 | Develop consultation options |  | 13
18 | Use SA Framework to appraise options |  | 8
Consultation on Options (optional - not necessary under Regulations)
19 | Consider consultation responses |  | 3
Draft Neighbourhood Plan
20 | Prepare draft Neighbourhood Plan document |  | 4
21 | Prepare SA Report |  | 6
22 | Prepare consultation materials |  | 3
Consultation on Draft Plan
23 | Consultation - minimum 6 weeks | 14 | 6
24 | Consider consultation responses |  | 3
Submission Neighbourhood Plan
25 | Prepare submission Neighbourhood Plan document |  | 5
26 | Prepare final SA Report |  | 5
27 | Prepare Consultation Statement |  | 4
Submission and consultation
28 | Submit relevant documents to MKC | 15 | 1
29 | MKC publicises submitted plan | 16 | 1
30 | Consultation - minimum 6 weeks | 16 | 6
Examination
31 | Examiner appointed |  | 3
32 | Documents and representations sent | 17 | 1
33 | Decide on hearing sessions or written representations only |  | 1
34 | If hearing sessions, advertise and hold sessions |  | 2
35 | Examiner's report published | 18 | 1
36 | Deal with any recommendations from Examiner's Report |  | 1
Referendum
37 | Organise Referendum, print ballot papers, advertise etc. |  | 8
38 | Referendum |  | 1
MKC adopts Plan
39 | MKC adopts Neighbourhood Plan | 19 | 1
40 | MKC publicises adoption of Neighbourhood Plan | 20 | 1
128